## IP-Revised2021
EATG Implementation Plan 2020 - 2022
Goal/Impact/Change | Outcomes 2025 | Outcomes 2022 | Activities | Outputs | Output 2020 | Output 2021 | Output 2022 | Indicator | Baseline | Target | Source | Resources (€, material, staff) | Extra Comments / clarifications/ context
QUALITY OF LIFE
Ending the AIDS epidemic by 2030 | Healthy communities of people living with and affected by HIV, with enhanced quality of life and access to effective, integrated health and support systems | (1) New and integrated models of care are identified, designed, developed, and promoted with community involvement | Review of R&D recommendations from Ageing with HIV project (especially addressing integrated care): defining new initiatives based on the recommendations, fundraising and implementation of new initiatives |  | project proposal: Frailtyand HIV: improving the QoL of an Ageing population | Mapping paper on prevention and mitigation tools on fraily;New funding agreement, new initiatives | New initiatives | Nr of new EATG initiatives identified addressing integrated models of care | 0 | 2 | R&D Recommendations from Ageing with HIV project
[8 empty] | Nr of new EATG initiatives implemented addressing integrated models of care | 0 | 1 | Project agreement; internal reports
|  |  | HIV & Mental health project |  | Logo and webpage, Literature review, survey, | workshop, webinar , briefing paper, Multi-stakeholder event, EACS guidelines meeting, industry meeting, newsletter European network, evaluation report, reporting to sponsors | (After project end-date) Maintaining European Network, further dissemination of project outcomes; follow-up actrivities identified | Nr of key findings supporting integration of mental health into HIV care | 0 | 5 | Literature review report
[8 empty] | Nr of recommendations published in the EATG briefing paper addressed by key stakeholders for integrating mental health into HIV care. | 0 | 5 | Briefing paper
|  |  | Contribution to HIV Outcomes initiative: input to meeting agendas, review of meeting minutes |  | Input into agendas and speaking at HIV outcomes WAD event | Input into agenda for and attendance at HIV outcomes initiative meetings | Input into agenda for and attendance at HIV outcomes initiative meetings | Nr of items on meeting agendas addressing integrated models of care with community involvement | 0 | 2 | HIV Outcomes Initiative Meeting agendas
[8 empty] | Nr of points raised by community integrated into event agenda planning | 0 | At least 1 per relevant meeting | HIV Outcomes Initiative Meeting minutes, agendas, presentations
|  |  | EmERGE project: Policy brief publication and dissemination, Multi-stakeholder meeting, Submission of deliverable reports on community meetings and guidelines, contributing to further development and sustainability of EmERGE mobile application through continued co-design process |  | Policy brief, multi-stakeholder meeting presentations and report, deliverable reports, MoU with EmERGE mHealth Ltd, abstracts | Co-design meetings based on MoU with EmERGE mHealth Ltd | Co-design meetings based on MoU with EmERGE mHealth Ltd | Nr of times EATG's recommendations (in policy brief addressed by key stakeholders promoting mHealth for increased integration of HIV care) are disseminated | 0 | 5 fora | Policy brief
|  |  | EmH : supporting continuing community co-design |  |  | support user groups |  | Community contribution in the co-design of the app | NO (not in the new set-up of the non-profit) | YES
|  |  | STEP UP Training modules addressing integrated models of care, local training modules, follow-up projects, reporting, fundraising |  | 20 online live training sessions in Russian and in English (2 hours per session) + exercises and reading assignments | 16 online online live training sessions in Russian and in English (2 hours per session) + exercises and reading assignments + F2F summer course (week end) + local trainings + 4 follow-up projects implemented via small grants 2021 | New funding for next STEP UP programme | Nr of training sessions addressing integrated care | 0 | 2 | STEP UP training session presentations, final report |  | the training model required adaptation due to COVID19 related restrictions
[8 empty] | Nr of national trainings addressing integrated care | 0 | 2 | STEP UP national trainings agendas and reports
[8 empty] | Nr of delivered follow-up projects addressing integrated care | 0 | 2 (dependent on local needs) | STEP UP follow up project reports
|  |  | European Red Umbrella Academy - Sex Work & HIV Advocacy Training Programme: Training module addressing integrated models of care, national trainings, position papers, final report, dissemination of project findings, fundraising |  | 8 online training sessions | 3 position papers, 6 national projects, reporting, dissemination of project findings, fundraising | Dissemination of project findings, fundraising | Nr of training sessions addressing integrated care | 0 | 2 | Training Programme presentations and final report |  | most likely to go online (decision pending as of 19 August)
[8 empty] | Nr of national trainings addressing integrated care | 0 | 2 | National training reports
[8 empty] | Nr of recommendations in the policy papers addressing integrated care | 0 | At least 1 | Policy papers
|  |  | Coordination and secretariat of EU Civil Society Forum on HIV, TB, Hep (stimulating the exchange of knowledge and knowhow between civil society organisations and with other actors): coordination team TCs, online and F2F meetings and communication via listserv, social media tools and through the European Health Policy Platform |  | CSF ToR , call for application, agendas, TCs minute etc | Agendas, TCs minutes, reports, letters etc | Agendas, TCs minutes, reports, letters etc | Nr of time agendas, reports, statements, address the issue of integrated models of care | O | 6 | CSF website; CSF reporting documents
|  |  | Advocacy: contribute to public policy and programme development (including funding) by channelling knowledge and expertise from local civil society to EU institutions, governments and international public health agencies via ECDC/WHO expert meeting, Civil Society Forum, HIV Outcomesand other project events |  | HIV Outcomes events agendas, CSF agendas/meeting reports; EPF and EPHA meeting agendas, conferences agenda (HIV Glasgow), partication in ECDC/WHO meetings | Presentations, submission to consultations, position papers/statements, input into documents, EU Civil Society Forum agendas/reports | Position/policy paper drawing on projects and member experience | Nr of policy documents, agendas, statements referring to our points (including our proposals as agenda point, good practice or conclusions) | 0 | 6 | External documents
[8 empty] | Nr meetings with and presentations to policy makers or key stakeholders on the topic to present EATG proposals | 0 | 6 | E-mails, outlook agendas, …
|  | (2) Healthcare service providers' awareness is increased about HIV-related stigma and discrimination and is acted upon | Step-up trainings addressing stigma and discrimination by healthcare workers. Local training and follow-up projects of STEP-UP with activities addressing stigma and discriminination by healthcare workers. |  | 12 online live training sessions in Russian and in English (2 hours per session) + exercises and reading assignments | 10 online online live training sessions in Russian and in English (2 hours per session) + exercises and reading assignments + F2F summer course (week end) + local trainings + 4 follow-up projects implemented via small grants 2021 | New funding for next STEP-UP programme | Nr of training sessions addressing stigma & discrimination | 0 | 1 | STEP-UP training session presentations, final report
[8 empty] | Nr of national trainings addressing stigma & discrimination | 0 | 1 | STEP-UP national trainings agendas and reports
[8 empty] | Nr of delivered follow-up projects addressing stigma & discrimination | 0 | 2 (dependent on local needs) | STEP-UP follow up project reports
|  |  | Mental Health Project. |  | literature review and survey | workshop/briefing paper/ Multi-stakeholder event | (After project end-date) Maintaining European Network, further dissemination of project outcomes; follow-up actrivities identified | Nr of key findings on S&D | 0 | 3 | Literature review report
[8 empty] | Nr of recommendations published in the EATG briefing paper addressed by key stakeholders for integrating mental health into HIV care. | 0 | 3 | Briefing paper
|  |  | Stigma & discrimination to be regularly discussed and solutions shared at CSF. |  |  | Agendas, TCs minutes, reports, letters etc | Agendas, TCs minutes, reports, letters etc | Nr of time agendas, reports, statement address the issue of integrated models of care | O | 3 | CSF website; CSF reporting documents
|  |  | Collect and share examples of U=U education/awareness raising in health care settings beyond HIV care within community and healthcare professionals |  |  | U=U education/awareness raising in health care settings beyond HIV care mapping paper + webinar
|  | (3) Community influences the development and implementation of digital solutions at local, national and regional level | EmERGE Project and input in EmH; Multi-stakeholder meeting & policy brief; HIV Outcomes WAD event ; CSF meetings, EPHA and EPF work on the subject |  | EATG position, EmERGE multi-stakeholder meeting agenda and report, HIV outcomes event, CSF meeting | n/a | n/a | Nr of documents, presentations, group discussions addressing digitalisation and design & development of e-technologies produced with the EATG input | 0 | 3 | Reports, meeting agenda
[8 empty] | Nr of EATG members providing input to the documents and participation at events and meetings on digitalisation/design & development of e-technologies | 0 | 20 | Meeting report
|  |  | COVID 19 community response project | investigation on opportunities and challenges on digitalisation Production of position statement on digitalisation Multi-stakeholder and expert meeting on and reccomendations | COVID 19 bulletins, HIV Glasgow community session, EmERGE COVID 19 session, Position statement end of 2020/21 |  |  | Opportunities,challenges, solutions identified and shared with stakeholders; community groups learn from each other accross countries and sectors | NO | YES | meeting report
[8 empty] | Position paper on opportunities and challenges being distributed | NO | YES | Paper
[8 empty] | Nr of recommandations being followed up upon by the participants | 0 | 5 | Reports
|  | (4) Rights violations in specific countries or sub-regions are monitored and reported | COVID 19 community response project; community monitoring and mobilising support in the case of human rights concerns at national level: via CSF, outreach |  | Community reporting via COVID 19 EATG bulletins and sharing of results with stakeholders | Community report | Community report | Nr of community reports per year | 0 | At least 3 | Report | Fundraising | the COVID 19 community response projects addresses these issues
|  | (5) Good practices on Health Technology Assessment (HTA) and community engagement are identified and promoted | Contribution to the development of HTA tools in the framework of the Paradigm Project |  | HTA set of tools | n/a | n/a | Nr of good practices on HTA identified | 0 | 6 | HTA set of tools
|  |  | Dissemination of set of tools developed by Paradigm through ECAB & other training, and translation into Russian |  | n/a | Training on HTA set of tools | n/a | Nr of trainings delivered | 0 | 1 | Training agenda
[5 empty] | Meetings, TCs | Meetings, TCs | Meetings, TCs | Nr of HTA agencies, nr of meetings | ? | ? | Meeting minutes
|  |  | Enhance EATG capacity on Health Technology Assessment (HTA) |  |  | internal training |  | Nr of policy meetings when paper is presented | 0 | 2 | Meeting minutes
|  | (6) Community members are equiped to influence pricing negotiations/engage on medicines shortages | STEP UP Training modules |  | 12 online live training sessions in Russian and in English (2 hours per session) + exercises and reading assignments | 10 online online live training sessions in Russian and in English (2 hours per session) + exercises and reading assignments + F2F summer course (week end) + local trainings + 4 follow-up projects implemented via small grants 2021 | New funding for next STEP- UP programme | Nr of training sessions addressing pricing negotiations/medicines shortages | 0 | 2 | STEP UP training session presentations, final report
[8 empty] | Nr of national trainings addressing pricing negotiations/medicines shortages | 0 | 2
[8 empty] | Nr of delivered follow-up projects addressing pricing negotiations/medicines shortages | 0 | 2 (dependent on local needs) | STEP-UP follow up project reports
COMBINATION-PREVENTION
Ending the AIDS epidemic by 2030 | Empowered affected communities working in collaboration, with access to the HIV, viral hepatitis, TB and STI prevention tools they need | (1) Increased community involvement in the development and promotion of innovative, sensitive, user-friendly diagnostics tools | reporting testing practices via the COVID 19 community response project |  | Surveys, bulletins, e-community meeting on self-testing, | Report and dissemination | Update | Nr of use of COVID 19 project results regarding testing practices | 0 | 30 | Partners website, social media analytics etc
|  |  | Production of videos on diagnostics, legal and regulatory issues, implemention, R&D etc - promotion via social media |  |  | Video | Video | Nr of participants and viewers of report/recording | 0 | 120 | Gotomeeting analytics? |  | to be revisited
|  |  | Presentations at community meetings, conferences |  | Abstracts, presentations | Abstracts, presentations, session at HepHIV, HIV Glasgow | Abstracts, presentations | Nr presentations, abstracts accepted | 0 | 6 | CSF evaluation form, conference websites
|  |  | Examine feasibility of pooled procurement of diagnostics or other means to make them more affodable outside of medical settings |  |  | internal report | Tbd | Nr of joint actions | 0 | 2 | Project report | Fundraising | to be revisited
|  |  | ECAB with diagnostics developers and manufacturers and community exchange meeting |  |  | Agenda, preparatory questions to companies, meeting report | Tbd | Nr of questions/concerns followed up on by pharmaceutical companies and community | 0 | 10 | Questions to companies, response at meetings and in follow up
|  |  | EuroTEST Steering committee participation (participation in SC and in core group for the COVID-19 impact assessment on testing in Europe |  | survey disseminated and one publication | Presentations/abstracts at hepHIV 2021 | Tbd | Nr of EuroTEST projects and actions EATG is involved in | 0 | 3 | EuroTEST annual report; project proposals
|  | (2) Community is involved in the development and implementation of innovative (biomedical) prevention technologies and programmes and their delivery models | PREP-IT (codesign, stakeholder engagement, communication) |  | Project proposal |  |  | Nr of community meetings and workshops, | 0 | At least 5 | Project documents | Fundraising
[8 empty] | Nr of community organisations involved | 0 | At least 5 | Project documents
|  |  | Organising dialogue between community and developers: dialogue on PREP/ or prevention technologies (ECAB: agenda, preparatory questions to companies, meeting report) |  | ECAB | ECAB | ECAB | Nr of concerns raised followed up upon | 0 | 4 | E-mail correspondance with companies, meeting reports (ECAB and bilateral) |  | ECAB on July 30 with Gilead, ViiV, MSD. 12 Questions were submitted and answered by the companies. 2 main items were in the agenda (R&D and response to COVID). There were no major follow up. Request of ViiV registrationn of CAB LA at EMA to follow up
|  |  | Community representation on HIV preventive vaccine trials and R&D: investigate existing/planed trials and if community is involved. |  | tbd | overview of relevant vaccines trials and community involvement | EATG members present in the main boards for vaccine trials | Nr of members involved in HIV trials on preventive vaccine | 0 | 5 |  | Fundraising | 1 member in EHVA board on preventtive vaccine (Harriet Langanke)
[8 empty] | Nr of members attending conference and meeting on preventive research | 0 | 15 (there maybe repetition in member attending)
[8 empty] | Nr of reports to members on preventive vaccines | 0 | 3
|  |  | Participation in PREP in Europe Initiative SC; input in PiEi initiatives and thematic meetings |  | PiEi Agenda with EATG input | PiEi Agenda with EATG input | PiEi Agenda with EATG input | Nr of EATG suggestions in Agenda | 0 | 3 meaningful changes | tbd
[8 empty] | Nr of EATG members participating in PiEi meetings and initiatives | 1 (official representative) | 10
|  | (3) Community’s capacity to respond to the needs of inadequately served populations is increased, by identifying and promoting evidence based combination prevention programmes | Chemsex Project: assessing interventions; defining quality standards; capacity-building; advocacy for public policy support for chemsex intervention following defined quality standards. |  |  | project proposal | Training workshops; abstracts, presentations, articles | Nr of community partners engaged in the project | Tbd | Tbd | Tbd |  | moved to 2021 - no capacity (time) to work on this
|  |  | Collaboration with ENPUD CAB |  |  | Needs assessment report | Follow-up action by community? | Identified needs | NO | YES | TBD | Fundraising | no capacity to work on this but it is addressed via the COVID Project
[8 empty] | Established partnerships | NO | YES | TBD
|  |  | STEP-UP training modules addressing prevention, local training modules, follow-up projects, final report, fundraising |  | 20 online live training sessions in Russian and in English (2 hours per session) + exercises and reading assignments | 4 online online live training sessions in Russian and in English (2 hours per session) + exercises and reading assignments + F2F summer course (week end) + local trainings + 4 follow-up projects implemented via small grants 2021 | New project proposal | Nr of training sessions addressing prevention | 0 | 1 | STEP-UP training session presentations, final report
[8 empty] | Nr of national trainings addressing prevention | 0 | 2 | STEP-UP national trainings agendas and reports
[8 empty] | Nr of delivered follow-up projects addressing prevention | 0 | 2 (dependent on local needs) | STEP-UP follow up project reports
|  |  | European Red Umbrella Academy- Sex work & HIV advocacy training programme: Training module addressing prevention, national trainings, position papers, final report, dissemination of project findings, fundraising |  | 8 online trainings | Tbd | Tbd | Nr of training sessions addressing prevention | 0 | 1 | Training programme presentations and final report |  | F2F training postponed to end october currently decision pending ICRSE to move the training online
[8 empty] | Nr of national trainings addressing prevention | 0 | 2 | National training reports
[8 empty] | Policy paper addressing combination prevention | NO | YES | Policy papers
|  | (4) Community concerns on the enabling legal environment, investment and implementation of combination prevention are reflected by international/regional policies and programmes | COVID 19 Community response project |  | 6 Community bulletins, e-mutual learning sessions and HIV Glasgow community session, abstracts, Facebook group ‘HIV/co-infections and COVID-19 Resources’ |  |  | our concerns reflected in stakeholders agendas, documents |  | 6
|  |  | Participation in the coordination of the EU Civil Society Forum on HIV, TB, hep (stimulating the exchange of knowledge and know-how between civil society organisations and with other actors): coordination team TCs, online and F2F meetings and communication via listserv, social media tools and through the European Health Policy platform |  | CSF ToR , call for application, agendas, TCs minute etc | Agendas, TCs minutes, reports, letters etc | Agendas, TCs minutes, reports, letters etc | Nr of time agendas, reports, statement address concerns and demands related to prevention | O | 6 | CSF website; CSF reporting documents
|  |  | Participation in CSF on Drugs |  | Submission to EU drug policy evaluation | tbd |  | Nr of time agendas, reports, statement address concerns and demands related to prevention | 0 | 3 | CSF website; CSF reporting documents
|  |  | Channelling knowledge and expertise from local civil society to EU institutions, governments and international public health agencies via ECDC/WHO expert meetings, civil society forum, NGO networks (EPHA, PICUM, EU4Health, CSF on Drugs, ACHIEVE), participation in EACS-ECDC-WHO standard of care project |  | Submission to EU drug policy evaluation; input UNAIDS paper on HIV and Migration, input into European Standards of Care project of ECDC/EACS | Input into European Standards of Care project of ECDC/EACS | Position/policy paper drawing on projects and member experience | Nr of policy documents, agendas, statements referring to our points | 0 | 10 | EC documents, agencies docs
|  | (5) Community is involved in the monitoring and reporting of treatment shortages as part of the treatment as prevention, PreP and harm reduction agenda | Monitoring continuity of care and prevention (HIV, TB, Hep, STIs meds, vaccines, diagnostics, OST) via surveys, online reporting, ppt, alerts, report from meeting with policy-makers |  | COVID 19 surveys, bulletins, abstracts, | Reporting & monitoring tool | 2nd Reporting & monitoring tool | Existence of tool | NO | YES |  | Fundraising | to be discussed with Alex Schneider, Mario and Frank at next Programme chair meeting
PARTNERS IN SCIENCE
Ending the AIDS epidemic by 2030 | Communities of people living with and affected by HIV engaged with all prospective and observational research processes in up-to-date diagnostics, medicines, medical devices and care relative to HIV, viral hepatitis, TB and STIs | (1) Community is engaged in the design, development and implementation of research/programmes for new therapeutic solutions | ECAB HIV (e.g. on long acting treatment, treatment for heavily treatment-experienced PLHIV, therapies for long term remission from HIV, cure programmes and prevention strategies) One ECAB on heavily treatment-experienced PLHIV; one ECAB on PrEP |  | 2 ECAB meetings; Reports and action points; M&E report on the impact of the meeting | 2 ECAB meetings; Reports and action points; M&E report on the impact of the meeting Creation of a pool of expert members and less expert members to invite to the meetings | 2 ECAB meetings; Reports and action points; M&E report on the impact of the meeting | Number of industry partners and other stakeholders involved | 0 | At least 4 different industry partners engaging per year | Internal records, minutes
[8 empty] | Number of agreed follow up actions completed | 0 | 80% of the follow up completed by the agreed deadlines | Internal records, minutes
[8 empty] | Level of success/satisfaction measured by the M&E report | 0 | 60% of overall satisfaction /success | M&E survey
|  |  | EATG contributes to the production of the HIV pipeline report |  |  | Agreement with iBase to collaborate on the Pipeline report | Pipeline report published in collaboration with EATG | Number of pipeline reports published | 0 | At least 1 reports published and disseminated | i-Base | Consultant - fundraising
[6 empty] | Pipeline translated into Russian | Pipeline translated into Russian | Number of translations produced | 0 | At least 2 translations published
|  |  | PROMise-project: Fundraising and revision of project plan, review of initiatives, developing a network of researchers, community research, training, multi-stakeholder meeting; developing framework document, newsletters, videos, publications and translated materials |  | Fundraising, revision of project proposal, communuty research, input from different stakeholders and developing a research network with them, publications | Fundraising, revision of project proposal, review of initiatives, training, multi-stakeholder meeting, publications | TBD | Report on community research on HIV-specific PROMs completed | NO | YES | PROMise project | Fundraising
[8 empty] | Nr of stakeholders involved | 0 | At least 3 | PROMise project
[8 empty] | Nr of community representatives involved in the research process | 0 | At least 10 | PROMise project
|  |  | Improved monitoring and update of the report “Clinical Trial Sites in Eastern Europe and Central Asia - HIV, Hepatitis C, Tuberculosis - Brief Landscape Review” from 2017 |  | Updated report on CT in EECA |  |  | Nr of additional sites identified | 240 | At least 260 | EATG mailing list, website | Consultant
[8 empty] | Nr of times the updated report is shared for advocacy purposes | 0 | 15 | comms with companies, regulator, other stakeholders
|  |  | Protocol reviews |  | At least 10 protocols or documents related to R&D reviewed by EATG members. | At least 10 protocols or documents related to R&D reviewed by EATG members Create a pool of less experienced members to join as observers | At least 10 protocols or documents related to R&D reviewed by EATG members | Number of protocols/ documents related to R&D reviewed by EATG | 1 | 30 | Protocol review table
[8 empty] | Number of community members involved in the review | 1 | 20 | Protocol review table
|  |  | Involvement of less experienced members in protocol reviews |  | At least 4 less experienced members involved in PR | At least 4 less experienced members involved in PR Creation of two pools: one of expert members and one of less experience members to be contacted for reviews | At least 4 less experienced members involved in PR | Number of less experienced reviewers involved as observer | 0 | At least 12 less experienced members receiving training per year | Protocol review table
|  |  | EATG members represent community and participate in external Scientific boards/ CABs |  | At least 5 members providing community input in other scientific boards | At least 5 members appointed in other scientific boards | At least 5 members appointed in other scientific boards | Number of community members appointed in other boards | 0 | 15 | representation table
|  | (2) Community needs, priorities and strategies for viral hepatitis, TB, and STI co-infection with HIV are defined with key stakeholders | ECAB on viral hepatitis / NASH |  |  | 1 ECAB on viral hepatitis; Reports and action points | 1 ECAB on viral hepatitis; Reports and action points | Number of follow-up points identified at the meetings | 0 | At least 1 | Internal records and minutes | consultant?
[8 empty] | % of actions point that are addressed after the meetings | 0 | At least 75% addressed | Internal records and minutes
[8 empty] | % of actions point that are not addressed after the meetings | 0 | Less than 25 % | Internal records and minutes
|  |  | Identifying Strategies and Partnerships on R&D Advocacy in TB | EATG will collaborate with TB advocates to bring the voice of the community regarding HIV/TB coinfection in the discussion on R&D |  | Strategic Meeting to define partnerships and activities with TB allies | EATG partnership and collaboration with TB allies estabilished | Nr of EATG members in the TB CAB or other TB treatment advocacy groups | 0 | At least one members in the TB CAB | Partners website, social media analytics etc
[8 empty] | Nr of Formal participations of EATG attendance as observers | at least 3 | At least one participation of EATG as observer per year | Partners website, social media analytics etc
|  |  | EU-Pearl Project |  | EATG providing input in EU Pearl | EATG providing input in EU Pearl | EATG providing input in EU Pearl | N of members in the patient advisory group/ providing input for TB, NASH or other trials | 0 | 5 | formal representation, exchanges on trial and input on research
|  |  | TB Online |  | EATG Providing input in TB Online Channel | EATG Providing input in TB Online Channel | EATG Providing input in TB Online Channel | Number of Issues on which EATG has provided input | 0 | 36 | Ana Balkandjeva
|  |  | Advocacy for R&D on viral Hepatitis |  |  | Streategy being developed Multistakeholder meeting report with clear action points | Development of a position paper on treatment needs for PLHIV/HBV | Number of events | 0 | at least 1 MS Meeting |  | Fundraising! Consultant
[8 empty] | Nr of key stakeholders involved |  | At least 3
[8 empty] | Nr of key stakeholders co-signing and adopting the PP |  | At least 5 partners
|  | (3) Community members have increased scientific knowledge on HIV and relevant co-infections | Capacity building of members |  | Pre-GA training on basic science delivered | At least two trainings: HIV and/or co-infections delivered | At least two trainings on HIV and/or co-infections delivered | Nr of members trained | 0 | At least 20 members receiving training per year | Pre and post survey | Consultant
|  |  | Contributing to the training activities of EUPATI (virtual conference and expert training course); Use of EUPATI toolbox material in EATG training (STEP-UP and ECAB); Contributing to the sustainability plan for EUPATI training through the EFOEUPATI project (review of new content, dissemination of project information) |  | Virtual conference presentation, training course presentation, presentations at ECAB and STEP-UP training, new material published in toolbox | Presentations at ECAB and STEP-UP training, new material published in toolbox | Presentations at ECAB and STEP-UP training, new material published in toolbox | Nr of EATG produced presentations based on EUPATI material | 0 | 5 | Presentations
[8 empty] | Nr of new EUPATI materials reviewed by EATG staff and members | 0 | 2 | Documents
|  | (4) Community understands and is engaged in cure and vaccine research | HIVACAR project deliverables: Conducting a psychosocial study, preparation of information materials and an online toolbox |  |  | 1 survey to all community members; 1 survey to clinical trial particpants | Report on psychosocial study, information materials | Nr of survey responses | 0 | 300 | Survey data; PS report | Comms
[8 empty] | Nr of participants showing increased knowledge | 0 | 50% (6 out of 12) | Survey data; PS report
[8 empty] | Nr of community members involved in PS report and comments on other documents | 4 | 10 | Survey data; PS Report
[6 empty] | Update online toolbox (HIVACAR) | n/a | Nr of users accessing the toolbox | 0 | 500 | Webpage analytics
|  |  | EHVA Project: organising community meeting; developing information materials with the input of community, reporting |  | Community meeting, information materials, report | Further dissemination of project outcomes | Further dissemination of project outcomes | Number of community members involved in the meeting | 0 | 10 | Participant list
[8 empty] | Number of members/staff involved in reviews of trial/material for the trial/ board | 1 | 15 | Participant list of community meeting
[8 empty] | Number of documents reviewed by members | 3 | 5 | Documents
|  |  | STEPS workshop on long-term remission from the HIV infection |  |  | 1 meeting at EACS Conference 2021 Report with main outcomes produced and disseminated and shared externally | 1 meeting at GLASGOW HIV Congress 2022 Report with main outcomes produced and disseminated externally | Number of meetings | 0 | 2 meetings | Conferences' networks and websites | Consultant - fundraising
[8 empty] | Number of attendees | 0 | 75 attendees in total | Meeting report
[8 empty] | Number of document disseminated | 0 | 3 | EATG mailing list
|  | (5) HIV Community is actively engaged in improving and promoting Patient Engagement in several disease areas - ADD R&D ELEMENT - WITH OTHER PARTNERS | PARADIGM: Development and implementation of the monitoring& evaluation framework for ECAB (WP3): Meeting with ECAB members and industry representatives, framework, revised application and feedback forms for ECAB, tracking tool and ECAB guidance document, pilot ECAB meetings using the new framework |  |  | ECAB specific M&E framework developed | ECAB meetings using the new framework | Nr of meetings with ECAB members and industry representatives | 0 | 3 | Slideset
[8 empty] | Number of other activities where the M&E framework is adopted by EATG (e.g. multi-stakeholder meetings) | 0 | 1 | M&E tracking tool
|  |  | PARADIGM: development of tools to facilitate patient engagement in R&D with different stakeholders (WP4) |  | Tools to facilitate patient engagement in R&D: Code of Conflict, Conflict of Interests, enhancement EUPATI guidelines and other tools and templates | n/a | n/a | Nr EATG documents used as reference/templates to create new tools | 0 | 4 | WP4 collaboration with other partners
[8 empty] | Number of topics developed with the direct contribution of EATG (as authors or main reviewers) | 0 | 2 | Paradigm pubblications
[8 empty] | Number of members involved in the authoring and review of material | 0 | At least 10 | contracts and email exchange with members
|  |  | PARADIGM: Participation in research and community engagement in the project |  | Publications from WP2, 3 and 6 where EATG is involved, scientific publications authored by EATG, Presentations at other Patient group events | n/a | n/a | Nb of members involved in the project activities on patient's engagement (in publications, development of materials, suistainability, participation to meetings) | 7 | 15 | Survey on knowledge/capacity on patient engagement
[8 empty] | Nb of EECA members involved | 2 | 2 | Survey on knowledge/capacity on patient engagement
[8 empty] | Existence of survey on knowledge/capacity on patient engagement | NO | YES | Survey on knowledge/capacity on patient engagement
|  |  | PARADIGM: EATG contribution to sustainability roadmap for future patient engagement (WP6) |  | Sustainability roadmap for future patient engagement | n/a | n/a | Nr of Incorporation of EATG contribution to the roadmap (based on responses to surveys and consultations by EATG members) | 0 | At least 1 | WP6
[8 empty] | Nr document or qualitative report aknowledging the role of EATG in designing the sustainability plan | 0 | At least 1
|  |  | PARADIGM: EATG contribution to translate the material into Russian and put it online (WP5) |  | PARADIGM material translated into Russian and available online | n/a | n/a | Nr document translated in Russian and uploaded online | 0 | 55 documents (spread over 9 topics)
|  |  | EATRIS+ : the project looks at a new approaches on clinical trials (for instance where different trials will run simultaneously in the same platform, or looking at the establishment of a European Network or research centres doing transnational medicines). |  |  | EATG activities needs to be define there are current negotiation with EPF. | EATG activities needs to be define there are current negotiation with EPF. | The indicators will be added once we have clarified the activities | TBD | TBD
Note: the section below is not part of the written external LTS, but focuses on organisational Development and hence has an internal focus
| The EATG is a 21st Century organisation, professional and ready for contemporary challenges | (1) EATG is restructured following the Programme Structure of its LTS | Creation, election, installment and functioning of new structures and bodies, as well as their evaluation. |  | Program Chairs; Program Committees; Task groups | New Program Chairs; Program Committees; Task groups, Evaluation of New Structure | New task groups; Evaluation Report on new structure | Existence of Program chairs & committees | NO | 3 Chairs and 3 committees | E-mails to members
[8 empty] | Nr of Task Groups | 0 | At least 6 Task Groups | E-mails to members
[8 empty] | Nr of meetings between Programme Managers, Programme Chairs (and Committees) | 0 | At least 12 PM-PC meetings per programme and 3 interprogramme meetings per year | Internal Reports; e-mails
[8 empty] | Nr of internal or self-evaluation about IP progress | 0 | One per year | Revised IP
|  | (2) EATG has proper tools, policies and procedures in place that allow for professionalism and transparency | Implementation and publication of new work rules and development of internal rules |  | Final new work rules and internal rules (delayed due to lack of follow-up by Securex) | Final work rules | n/a | Publication, sharing and display of new work rules and internal rules in office | NO | YES | Internal documentation
|  |  | New staff/consultancy contracts in line with Securex Audit |  | New contracts for all staff/consultants |  |  | Nr of new contracts | 0 | 10 | Internal documentation
|  |  | Updated Terms of Reference for all staff/consultancy positions |  | New ToR's attached to all contracts | ToR ED to be finalised |  | Nr of new ToRs | 2 | 11 | Internal documentation
|  |  | Creation of online timesheets |  |  | New system in place |  | No. of online timesheets | 0 | 11 | Internal documentation
|  |  | Install software designed to support paperless bookkeeping |  |  | New system in place |  | Cost claims received in paper | 50% | 10% | Internal documentation
|  |  | Organisation of individual/collective trainings for staff members, in line with specific needs. |  | Evaluation and training programmes devised. | Evaluation and training programmes devised. New system in place. | New system in place | Capacity reinforcement plan | NO | YES | Training certificates, training invoices; training modules; exchanges with mentors.
|  |  | Development of a member recruitment strategy |  | Evaluation | New adapted strategy | Continuously adapted strategy | Existence of strategy | NO | YES | Internal documentation
|  |  | Review of constitution, operational guidelines, BoD manual |  | Composition of Overhaul Team. Implementing the overhaul motion (GA 2019). | Update of parts of constitution and OG that were not concerned by the Overhaul Motion (GA2019) | New Constitution and OG | Existence of new OG and constitution | 0 | 2 | Internal documentation
|  |  | Development of a Conflict of Interest Policy |  | Evaluation | New CoI Policy |  | Existence of COI policy | 0 | 1 | Internal documentation
|  |  | Evaluation and adaptation of the different EATG bodies |  | n/a | Evaluation | New ToR for DMAG, IA, Ombudspeople | Existence of new ToR | NO | YES | Internal documentation
|  |  | Development of an Anti-Corruption Policy |  | n/a | Anti-Corruption Policy |  | Existence of Anti-Corruption Policy and main responsible person(s) for follow-up | NO | YES
|  |  | Development of a climate plan that helps to reduce EATG's carbon footprint |  | Data collected (delayed due to Covid-19) | Data collected | Specific EATG guidelines on CO2 emission | Existence of guidelines | NO | YES | Internal documentation
|  |  | Development of an HR Manual as well as a new Staff Manual |  |  | HR Manual & Staff Manual |  | Existence of manuals | NO | YES
|  |  | Development of guidelines of written reports for contracted consultants and volunteers |  |  | Guideline document | Review of guideline document | Existence of guidelines | NO | YES |  |  | Could be expanded to guidelines for staff as well
|  | (3) EATG has a sustainable and diversified income stream | EATG actively seeks multi-year funding |  | Multi-year grants approved | Multi-year grants approved | Multi-year grants approved | Nr of multi-year grants | 1 | 5 |  |  | Successful for ViiV and Gilead
|  |  | EATG customises reporting to funders: additional to overall report, also one pager with some facts and figures for each main funder |  |  | Individual funders reports | Individual funders reports | No. of individual reports | 0 | 4 |  |  | year-end
|  |  | Create project proposals that are easily broken into segments depending on funding amounts and funders interests |  | New "segmented" project proposals | New "segmented" project proposals | New "segmented" project proposals | No. of new "segmented" project proposals | 1 (Mental Health) | 6 (2 per year)
|  |  | Development of joint (non-EC) projects in collaboration with other organisations |  | Projects with other organisation(s) (delayed due to Covid-19) | Projects with other organisation(s) | Projects with other organisation(s) | No. of projects with other organisationa
|  |  | EATG holds one stakeholder / fundraising event per year |  | Event (delayed due to Covid-19) | Event | Event | No. of stakeholder events | 0 | 3
|  |  | Creation of a case for support document/video to outline why EATG is uniquely qualified to tackle specific problems (USP) |  |  | Document produced and in use |  | Case for support document | NO | YES
|  | (4) EATG members in all their diversity have increased knowledge and capacities for patient engagement, science and HIV related advocacy and activism | Development of training program and system of mentors for new members |  | First training modules developed | Training modules and system in place. Evaluation |  | Nr of new members participating in training modules | 0% | 75% of new members | Attendance lists
[8 empty] | Nr of mentors assigned to new members | 0 | at least one mentor per member | DMAG
|  |  | All trainings/events organised by EATG, strive for diversity in participation, with special attention to age/experience, gender, geography, key populations. |  | All trainings better reflect the composition of the membership when relevant | All trainings better reflect the composition of the membership when relevant | All trainings better reflect the composition of the membership when relevant | % of key populations participating to internal trainings/events | % lower than actual reflection of membership compositions | TBD | Attendance lists
|  |  | All events and conferences to which EATG attends, strive for diversity in participation, with special attention to age/experience gender, geography, key populations. |  | All events/conferences better reflect the composition of the membership when relevant | All events/conferences better reflect the composition of the membership when relevant | All events/conferences better reflect the composition of the membership when relevant | % of key populations participating to external conferences/events | % lower than actual reflection of membership compositions | TBD | Attendance lists
|  |  | Involvement of less experienced members in various activities (protocol reviews, presenting,development of projects…) |  | At least 4 less experienced members involved in various activities | At least 4 less experienced members involved in PR | At least 4 less experienced members involved in PR | Number of less experienced members involved as observer | 0 | At least 12 less experienced members receiving training per year | Protocol review table
|  |  | Collection of data/statistics regarding the diversity of the membership, taking into account best practices on diversity and inclusion statistics (and recommendations on outreach to under-represented communities?) |  | Updated EATG membership application form | reliable data and statistics |  | Existence of reliable data on diversity | NO | YES | Membership statistics
|  |  | Based on the data collected (see above), development of specific activities, indicators and tools that respond to the data and enhance diversity, e.g. safer space guidelines, trainings, facilitation tools. |  |  | Specific activities, indicators and tools that respond to the data and enhance diversity | Specific activities, indicators and tools that respond to the data and enhance diversity | TBD | TBD | TBD | TBD
|  |  | EATG strives for bilingual (English-Russian) internal communication with members |  | Communication from the office on the memberslist is translated using Online Translator. | Communication on the memberslist from the office and internal bodies is translated using Online Translator. | Communication on the memberslist from the office and internal bodies is translated using Online Translator. | % of communication on members list that is translated | 0% | 100%
|  |  | Translation of EATG's main guiding documents into Russian |  |  | EATG's Travel and Finance Manual is translated into Russian. | EATG's Constitution and Operating Guidelines are translated into Russian. | Existence of translated documents. | NO | YES
|  | (5) EATG pays specific attention to domains and geographical areas where the HIV/Hep/TB epidemic is most severe | Development of project proposals with focus on EECA Region |  | Project proposal | Project proposal | Project proposal | Nr of project proposals | 0 | At least 1 per year | Donor websites/e-mails to donors
|  |  | Development of project proposals with focus on key populations/ stigma/discrimination |  | Project proposal | Project proposal | Project proposal | Nr of project proposals | 0 | At least 1 per year | Donor websites/e-mails to donors
|  |  | Technical assistance and capacity building for organisations/members from EECA? |  | Step-Up Training modules - 24 live online training sessions in Russian (2 hours / session ) | Step-Up Training modules & other trainings & follow-up projects - 20 live online training sessions in Russian (2 hours /session) | Step-Up Training modules & other trainings & follow-up projects | Nr of trainings/training modules and follow-up projects for organisations/members from EECA | 0 | At least 3 modules/trainings per year + 5 local trainings + 3 follow-up projects
|  |  | EATG - Implementation Plan 2020-22_narrative_EN |  | Policy initiative/campaign | Policy initiative/campaign | Policy initiative/campaign | Nr of policy initiatives/campaigns | 0 | At least 2 per year | EATG website, mailing lists
|  | (6) EATG's internal and external communications are effective and efficient | Development of new website |  | New website (delayed due to Covid-19) | New website | Website updated | Functioning website online | NO | YES | The internet
[8 empty] | Nb of visits to website | 0 (Old Website Jan-June 2019: aprox. 5000 visits/month) | 5000-7000 visits/month | Website statistics / Google Analytics
|  |  | Creating membership area within existing website |  | New membership area (delayed due to Covid-19) | New membership area | Membership area updated | % of members using the membership area within the website | 0 | 25% | Website statistics
|  |  | Reform of IT set-up with EATG e-mails, mailing lists, internal exchange, … (based on Office 365 or other software) |  | Appropriate use of EATG e-mail addresses | New mailing list & internal exchange system | IT reform completed | Nb of EATG e-mail addresses | 85 | 25 (BoD + Chairs + Staff + EMA?) | EZOShosting
[8 empty] | Capacity of EATG to create, delete, manage its own mailing list | NO | YES | Office 365
|  |  | Increased investment on social media and internet presence to maximise activism |  | Regular updates across EATG's SME (social media) and NME (native media: website) : Facebook - Twitter - LinkedIn - Instagram - Website (EATG news) - News Bulletin | As 2020 + 1 Instagram campaign | As 2021 + 1 cross-media campign | Social media metrics: followers likes engagment rates | January 2020 (aprox.): FB page likes: 2000 TW followers: 1850 LI followers: 60 IG followers: 160 EATG Newsletter subscribers: 330 News Bulletin: 270 | FB: + 10%/year TW: + 10%/year LI: + 30%/year IG: + 30%/year NL: + 10%/year NB: + 10%/year | SME metrics
|  | (7) EATG has a strong and reliable network of local and international partners | Evaluation of all local and international partnerships; renewal of relevant partnerships; ending of less relevant partnerships; identification of new relevant partnerships. |  | Evaluation of partnerships at governance meeting (delayed due to Covid-19) | Evaluation of partnerships at governance meeting. Renewal/ending/signing of new partnerships | Renewal/ending/signing iof new partnerships | Existence of partnerships | 5 paying partnerships | Relevant partnerships | MoU, payment, contracts, collaboration agreements
|  |  | Identification, meeting and possible collaboration with local partners in Brussels/Belgium |  | Exploratory and introductory meeting (delayed due to Covid-19) | Exploratory and introductory meeting | Joint event/collaboration (e.g. at Pride or World AIDS Day) | Existence of joint event/collaboration | 0 | 1 | Minutes, social media, websites
|  | 8) EATG concerns are reflected in regional policy, and guideline documents | Co-coordination of CSF on HIV, TB and Hep, participation in CSF on Drugs, input in WHO RCC, input into WHO action plans on HIV, TB and hep, WHO HIV health sector strategy update, WHO guidelines, input into ECDC guidelines; EPHA, EPF work , EU4Health Coalition, HIV Outcomes, ACHIEVE, NLO |  | letter to EU, csf meetings | 3 csf meetings reports, positions | 3 csf meetings, reports, positions | the following documents reflect our concerns/policy 'asks's: EU health programme regulation covers HIV and annual work programme; -Consolidated guidelines on viral hepatitis prevention, testing and treatment • Guidelines on comprehensive HIV and hepatitis services for Key Populations • Person-centred broader healthcare focus, equal focus on HIV, hepatitis and STI • Modules by population, behavioural interventions, innovatives service delivery models • STI guidelines • Consolidated guidelines on ARV use for prevention and treatment of HIV 08/12/2020 infection | 0 | 9 CSF meetings, 3 reports, 6 advocatedpositions